## Tasks
E-COMMERCE PROJECT ¦ 3 Hours/Day Schedule
54 Tasks ¦ 63 Hours ¦ 21 Days ¦ React + NestJS + MongoDB
# | Phase | Task | Details | Stack | Hrs | Day | Depends | compeleted
1 | Phase 1 | Project Setup | Init NestJS, React+Vite, GitHub, .gitignore | Both | 1.5 | 1 | —
2 | Phase 1 | MongoDB Setup | Create Atlas cluster, .env config | BE | 1 | 1 | #1
3 | Phase 1 | NestJS Pipes/Filters | ValidationPipe, HttpExceptionFilter | BE | 1 | 1 | #2
4 | Phase 1 | User Schema | Create User schema, auth module | BE | 1.5 | 2 | #3
5 | Phase 1 | Password Hashing | Bcrypt install, hash/compare | BE | 0.5 | 2 | #4
6 | Phase 1 | JWT Login | JwtModule config, login endpoint | BE | 1.5 | 2 | #5
7 | Phase 1 | Auth Guards | JwtAuthGuard, RolesGuard, decorator | BE | 1.5 | 2 | #6
8 | Phase 1 | Register Endpoint | Registration, email validation | BE | 1 | 2 | #7
9 | Phase 1 | React+Vite | Vite init, React Router setup | FE | 1.5 | 3 | #1
10 | Phase 1 | Axios Instance | Base URL, JWT interceptor | FE | 1 | 3 | #9
11 | Phase 1 | Auth Store | Zustand authStore, localStorage | FE | 1 | 3 | #10
12 | Phase 1 | Login/Register Pages | Form components, validation | FE | 1.5 | 3-4 | #11
13 | Phase 1 | Route Guards | ProtectedRoute, AdminRoute | FE | 1 | 4 | #12
14 | Phase 1 | Auth E2E Test | Register→Login→Token→/auth/me | Both | 2 | 5 | #13
15 | Phase 2 | Category CRUD | Schema, all CRUD endpoints | BE | 1.5 | 6 | #14
16 | Phase 2 | Category Test | Test endpoints with Postman | BE | 0.5 | 6 | #15
17 | Phase 2 | Product Schema | Schema with relationships | BE | 1.5 | 7 | #15
18 | Phase 2 | Product GET | GET endpoints, pagination, filter | BE | 1.5 | 7 | #17
19 | Phase 2 | Product Write | POST/PATCH/DELETE, role guards | BE | 1.5 | 8 | #18
20 | Phase 2 | Product Search | MongoDB text index, search params | BE | 1 | 8 | #19
21 | Phase 2 | Cart Schema | Cart with embedded CartItem | BE | 1 | 9 | #20
22 | Phase 2 | Cart Endpoints | Add/update/remove/get cart | BE | 1.5 | 9 | #21
23 | Phase 2 | Cart Clear | Clear logic, checkout integration | BE | 0.5 | 9 | #22
24 | Phase 2 | Order Schema | Order schema, snapshot logic | BE | 1 | 10 | #23
25 | Phase 2 | Place Order | Create order from cart | BE | 1.5 | 10 | #24
26 | Phase 2 | Order Query | GET orders, order details | BE | 1 | 10 | #25
27 | Phase 2 | Home & Grid | Home page, product grid | FE | 1.5 | 11 | #14
28 | Phase 2 | Product Detail | Product detail page | FE | 1 | 11 | #27
29 | Phase 2 | Search/Filter UI | Search input, category filters | FE | 1 | 11 | #28
30 | Phase 2 | Cart Store | Zustand cart, persistence | FE | 1 | 12 | #29
31 | Phase 2 | Cart UI | CartPage, CartDrawer components | FE | 1 | 12 | #30
32 | Phase 2 | Checkout Page | Order review, confirm | FE | 1 | 12 | #31
33 | Phase 2 | Orders List | User order history | FE | 1 | 12-13 | #32
34 | Phase 2 | Order Detail | Order detail view | FE | 0.75 | 13 | #33
35 | Phase 2 | Admin Products | Admin CRUD page | FE | 1.5 | 13 | #34
36 | Phase 3 | Stripe Setup | Stripe SDK, keys config | BE | 0.75 | 14 | #35
37 | Phase 3 | Stripe Checkout | Checkout session endpoint | BE | 1.25 | 14 | #36
38 | Phase 3 | Stripe Webhook | Webhook handler, confirmation | BE | 1.5 | 14 | #37
39 | Phase 3 | Stripe Frontend | Payment form component | FE | 1.5 | 15 | #38
40 | Phase 3 | Success/Cancel | Success/cancel pages | FE | 1 | 15 | #39
41 | Phase 3 | Loading States | Skeleton loaders, spinners | FE | 1 | 16 | #40
42 | Phase 3 | Empty States | Empty state components | FE | 1 | 16 | #41
43 | Phase 3 | Toast System | Toast/alert system | FE | 1 | 16 | #42
44 | Phase 3 | Mobile | Mobile responsiveness | FE | 1.5 | 17 | #43
45 | Phase 3 | Accessibility | ARIA, keyboard nav | FE | 1 | 17 | #44
46 | Phase 3 | Seed Script | Faker-js seed data | BE | 1 | 18 | #45
47 | Phase 3 | README | Comprehensive README | Both | 1.5 | 18 | #46
48 | Phase 3 | Swagger Docs | @nestjs/swagger setup | BE | 1.5 | 18 | #47
49 | Phase 4 | Deploy Backend | Railway/Render deploy | BE | 1.5 | 19 | #48
50 | Phase 4 | Backend Verify | Test production API | BE | 0.75 | 19 | #49
51 | Phase 4 | Deploy Frontend | Vercel/Netlify deploy | FE | 1 | 20 | #50
52 | Phase 4 | Frontend Verify | Test production frontend | FE | 0.5 | 20 | #51
53 | Phase 4 | Smoke Tests | Test critical flows | Both | 2 | 21 | #52
54 | Phase 4 | Final Polish | Bug fixes, cleanup | Both | 1 | 21 | #53
DAILY SCHEDULE TIPS
✓ Pick same time daily (morning recommended)
✓ Read task fully before starting
✓ Check dependencies - ensure #N is done first
✓ Use Postman to test API before frontend
✓ Commit each task to GitHub
✓ Days are estimates - adjust pace as needed